## Menu
Welcome to the Agile Project Team Workbook!
Hello Fellow Agilist!
The purpose of this template is to provide
a simple view of how an Agile project can be
tracked. Most teams who already have tools
should use this to guide them on how to
customize the tool to provide this information.
If you have no tool yet you may use this to track
a simple project BUT this is not a scalable
solution! So once you're past doing a Pilot and want
to deploy agile beyond one or two teams you should
consider using a tool to support your effort.
Sally@AgileTranformation.com
|  | Business Rules | Impediments | Retrospective | Team's Done
|  | Deliverables |  |  | Dependency
Designed by Sally Elatta - www.AgileTranformation.com
Dropdown List Legend
| Task Types | Status Types | Goals | Severity | Backlog Status | Status
| Analysis | To Do | Done | H | Backlog | Open
| Dev | Progress | Carryover | M | Current | Resolved
| Testing | Blocked | Not Done | L | Done
| DB | Done | Progress |  | New
| Doc | Cancelled | Cancelled |  | Cancelled
Action Item
Instructions
Go to Format -> Sheet -> Unhide to review any sheets (tabs) that are not visible.
Macros must be enabled in order to take advantage of all features.

## Backlog
The Backlog Tab: Goal is to provide a simple view of the Features and Stories on one single backlog list. We also see the story points and any change management notes. The bottom has total initial scope and tracks how many new stories were added so we can measure scope changes.
Rank | Story | Story Points | Release # | Business Value | Change Management Notes (comments relating to a story point chaning, new story added or a story removed)
Web Portal Site
1 - Security
1 | 1.1 As a Customer I want to Login so that I can access my account | 2 | 1 | High
2 | 1.2 As a Customer I want to register for new online account so I can access my information | 3 | 1 | High
| 1.3 Customer retrives forgotten password | 3 | 1 | Medium
| 1.4 Customer adds password hint | 2 | 2 | Low | Cancelled this story on 12/22 due to product owner request. Will send email to customer service to get password reset.
2 - Profile Management
3 | 2.1 Customer creates new profile | 5 | 1 | Medium
| 2.2 Customer updates existing profile information | 2 | 1 | Medium | This was a 5 and was re-estimated during the retropsective to 2 because the team found that most of the work was already done in 2.1.
3 - Place Order
4 | 3.1 As a Customer I want to search the product list so that I can find what I want. | 3 | 1 | High
| 3.2 Customer browses all products | 2 | 1 | High
5 | 3.3 Customer adds product to cart | 5 | 1 | High
| 3.4 Customer completes order | 8 | 1 | High
| * 3.5 Customer views product reviews | 5 | 1 | Medium | Added this story during iteration 2. Product Owner approved on dd/mm/yy
4 - Order Maintenece
| 4.1 Customer checks order status | 2 | 1 | High
| 4.2 Customer cancels recent order | 2 | 1 | Low
| 4.3 Customer searchs order history | 3 | 1 | Medium
100 - Non Functional Stories
| 100.1 Migrate customer data from legacy system to new oracle db | 8 | 1 | High
| 100.2 Develop High Level Architectural diagram for new system | 2 | 1 | High
| 100.3 Develop high level ERD and Logical database diagrams. | 3 | 1 | High
| 100.4 Develop High Level business process models | 2 | 1 | Medium
| 100.5 Design look and feel for site and high level site navigation prototype | 3 | 1 | High
| Original Story Points for Release 1 | 58
| New Points for Release 1 | 7
| Total Points for Release 1 | 65 | 10.77% |  | Change in scope
* Red = New Story Added
Red BOLD Story Point = Changed the Story Point
Crossed Out = Removed this Story
Sample Business (Non IT) Backlog
A - Vendor Selection
A1- As a … I want to develop the RFP we will submit for vendor selection so that our needs and qualifications are shared with potential vendors.
1.1 as a …. I want to develop/brainstorm the list of catagories to include in the RFP
1.2 as a .. I want to identify the stakeholder departments affected so I can invite them
1.3 as a .. I want to include questions and requirements from the ABC dept
1.4 as a … I want to develop initial draft of RFT
1.5 as a … I want to review the RFP and gain consensus on final draft
A2- As a … I want to submit the RFP to the potential vendors so they can respond to it.
A3- As a … I want to select our top vendor based on their RFP responses so we can move forward with the contracting processes.
B - Contracting

## Release Plan
This is a powerful view of the release plan on a project. It shows each iteration plan in detail and answers: what stories are planned, what is the target for each story, what was the actual outcome, who is the owner/manager of that story. How does are target vs actual velocity look? how are we doing overall? Release Burnup Tab links to this one for it's data.
Setup Iteration
ITERATION PLANNING | STORIES |  |  | STORY POINTS | Owner |  | STORY GOAL |  | DEMO & RETROSPECTIVE
[7 empty] | Target | Actual
| 100.1 Migrate customer data from legacy system to new oracle db |  |  | 8 | JoAnne Smith |  | Done | Not Done
| 100.2 Develop High Level Architectural diagram for new system |  |  | 2 | Greg Smith |  | Done | Done
| 100.3 Develop high level ERD and Logical database diagrams. |  |  | 3 | Doug Smith |  | Done | Done
| 100.4 Develop High Level business process models |  |  | 2 | Doug Smith |  | Done | Done
| 100.5 Design look and feel for site and high level site navigation prototype |  |  | 3 | Beth Smith |  | Done | Done
Setup Iteration Story Points | [5 empty] | Iteration | 18 | 10
[6 empty] | Cumulative | 18 | 10
Iteration Cost | [5 empty] | Iteration | 90000 | 85000
[6 empty] | Cumulative | 90000 | 85000
ITERATION 1 (July 1st - 22nd)
ITERATION PLANNING | STORIES |  |  | STORY POINTS | Owner |  | STORY GOAL |  | DEMO & RETROSPECTIVE
[7 empty] | Target | Actual
| 1.1 As a Customer I want to Login so that I can access my account |  |  | 2 | Larry |  | Done | Not Done
| 1.2 As a Customer I want to register for new online account so I can access my information |  |  | 3 | Adam |  | Done | Not Done
| 1.3 Customer retrives forgotten password |  |  | 3 | Mary |  | Done | Done
| 2.1 Customer creates new profile |  |  | 5 | Adam |  | Done | Done
| 2.2 Customer updates existing profile information |  |  | 2 | Mary |  | Done | Done
| 100.1 Migrate customer data from legacy system to new oracle db |  |  | 8 | Larry |  | Done-Carryover | Done
Iteration #1 Story Points | [5 empty] | Iteration | 15 | 18
[6 empty] | Cumulative | 33 | 28
Iteration Cost | [5 empty] | Iteration | 90000 | 93000
[6 empty] | Cumulative | 180000 | 178000
ITERATION 2 (July 22nd - Aug 12th)
ITERATION PLANNING | STORIES |  |  | STORY POINTS | Owner |  | STORY GOAL |  | DEMO & RETROSPECTIVE
[7 empty] | Target | Actual
| 3.1 As a Customer I want to search the product list so that I can find what I want. |  |  | 3 | Adam |  | Done | Done
| 3.2 Customer browses all products |  |  | 2 | Larry |  | Done | Done
| 3.3 Customer adds product to cart |  |  | 5 | Mary |  | Done | Done
| 3.4 Customer completes order |  |  | 8 | John |  | Done | Not Done
| * 3.5 Customer views product reviews |  |  | 5 | Greg |  | Done | Not Done
| 1.1 As a Customer I want to Login so that I can access my account |  |  | 2 | Larry |  | Done-Carryover | Done
| 1.2 As a Customer I want to register for new online account so I can access my information |  |  | 3 | Larry |  | Done-Carryover | Done
Iteration #2 Story Points | [5 empty] | Iteration | 23 | 15
[6 empty] | Cumulative | 56 | 43
Iteration Cost | [5 empty] | Iteration | 90000 | 110000
[6 empty] | Cumulative | 270000 | 288000
ITERATION 3 (Aug 12th - Sept 2nd)
ITERATION PLANNING | STORIES |  |  | STORY POINTS | RESOURCES |  | STORY GOAL |  | DEMO & RETROSPECTIVE
[7 empty] | Target | Actual
| 4.1 Customer checks order status |  |  | 2 | Jackie Smith, Alan Smith |  | Done | Done
| 4.2 Customer cancels recent order |  |  | 2 | Greg Smith, John Smith |  | Done | Done
| 4.3 Customer searchs order history |  |  | 3 | Greg Smith, John Smith |  | Done | Not Done
| 3.4 Customer completes order |  |  | 8 | Greg Smith, John Smith |  | Done-Carryover | Not Done
| * 3.5 Customer views product reviews |  |  | 5 | Greg Smith, John Smith |  | Done-Carryover | Done
#REF!
Iteration #3 Story Points | [5 empty] | Iteration | 7 | 9
[6 empty] | Cumulative | 63 | 52
Iteration Cost | [5 empty] | Iteration | 90000 | 120000
[6 empty] | Cumulative | 360000 | 408000
ITERATION 4 (Sept 2nd - 23rd)
ITERATION PLANNING | STORIES |  |  | STORY POINTS | RESOURCES |  | STORY GOAL |  | DEMO & RETROSPECTIVE
[7 empty] | Target | Actual
| 4.3 Customer searchs order history |  |  | 3 | Greg Smith, John Smith |  | Done-Carryover | Done
| 3.4 Customer completes order |  |  | 8 | Greg Smith, John Smith |  | Done-Carryover | Done
| 1.4 Customer adds password hint |  |  | 3 |  |  | Done | Done
Iteration #4 Story Points | [5 empty] | Iteration | 3 | 14
[6 empty] | Cumulative | 66 | 66
Iteration Cost | [5 empty] | Iteration | 90000 | 80000
[6 empty] | Cumulative | 450000 | 488000
Sept 23rd - Oct 7th
Hardening Iteration (Regression / Integration /Performance/Beta Testing )
Pre-Release Iteration (Oct 7th - Oct 28th)
PRODUCTION | FINAL USER TRAINING PROJECT TRANSITION HELP DOCUMENTATION REGRESSION AND INTEGRATION TESTING USER ACCEPTANCE & SIGNGOFF
Iteration Cost | [5 empty] | Iteration | 90000 | 80000
[6 empty] | Cumulative | 540000 | 568000
2011-10-31
Move to Production

## Release Burnups
These are powerful charts you can show to your business product owner (and to the team) to track progress. The Earned Value tracks how many story points were actually delivered compared to the team's target. It also tracks the very important SCOPE line which tracks total backlog points and measures any changes to it. The Cost tracks traget vs actual dollar burn in addition to the funding line that tracks how much we were funed for and any funding increases over time. The bottom graph tracks number of defects and impediements per iteraiton. Defects are bugs found during regression testing.
|  | Start | End | Targeted | Actual | Projected | Total Story Pts |  | Start | End | Targeted | Actual | Projected | Total Funding
| Iteration 0 | 0 | 0 | 18 | 10 |  | 58 | Iteration 0 | 2007-11-19 | 2007-12-11 | 90000 | 85000 |  | 450000
| Iteration 1 | 0 | 0 | 33 | 28 |  | 58 | Iteration 1 | 2007-12-12 | 2008-01-01 | 180000 | 178000 |  | 450000
| Iteration 2 | 0 | 0 | 56 | 43 |  | 63 | Iteration 2 | 2008-01-02 | 2008-01-30 | 270000 | 288000 |  | 450000
| Iteration 3 | 0 | 0 | 63 | 52 |  | 63 | Iteration 3 | 2008-01-31 | 2008-02-20 | 360000 | 408000 |  | 550000
| Iteration 4 | 0 | 0 | 66 | 66 |  | 66 | Iteration 4 | 2008-02-21 | 2008-03-12 | 450000 |  |  | 550000
| Pre-Release | 2008-03-29 | 2008-04-19 |  |  |  |  | Pre-Release | 0 | 2011-10-31 | 540000 |  |  | 550000
(We can also create a burn up chart that would show actual business value using Business Value Points. Email me for more information Sally@AgileTransformation.com)
[6 empty] | 82.54% | [6 empty] | 74.18%
|  | Start | End | Bugs | Impediments
| Iteration 0 | 2008-05-01 | 2008-06-30 | 0 | 0
| Iteration 1 | 2008-07-01 | 2008-07-25 | 5 | 9
| Iteration 2 | 2008-07-28 | 2008-08-22 | 3 | 0
| Iteration 3 | 2008-08-25 | 2008-09-19 | 4 | 6
| Iteration 4 | 2008-09-22 | 2008-10-17
| Iteration 5 | 2008-09-22 | 0
| Totals: |  |  | 12 | 15
Note on C44: Mutual of Omaha: Identify the start date planned for Iteration 0 and manually enter.
Note on C45: Mutual of Omaha: Link the start date back to the Release Plan worksheet for each iteration or manually enter.
Note on D44: Mutual of Omaha: Identify the end date planned for Iteration 0 and manually enter.
Note on D45: Mutual of Omaha: Link the end date back to the Release Plan worksheet for each iteration or manually enter.
Note on E44: Mutual of Omaha: Iteration 0 will not have stories or story points.
Note on E45: Mutual of Omaha: Link the Targeted Story Points back to each iteration's cumulative target story points in the Release Plan worksheet or manually enter.
Note on E51: Mutual of Omaha: % Done = Total Actual story points divided by Total Targeted story points.
Note on F44: Mutual of Omaha: Iteration 0 will not have stories or story points.
Note on F45: Mutual of Omaha: Link the Actual Story Points back to each iteration's cumulative actual story points in the Release Plan worksheet or manually enter.
Note on G44: Mutual of Omaha: Manually enter the total number of story points identified for the release. If the total number of story points changes between iterations, reflect the change for the iteration that it applies to.
Story Points Delivered
COST
Current Project % Done
Current Project % Burn
Project Quality & Impediments

## Metrics
Visit the site above to try the Test Drive for AgilityHealth. The TeamHealth Retrospective Assessment is facilitated by a certified AgilityHealth Facilitator (external or internal to your company).
You can view the schedule for upcoming certification courses from the site above or email Trisha@AgileTransformation.com

## Learning Agile
Are YOU ready to learn Agile NOW?
Click Here to Download our Agile Learning Roadmap
Agile Webinars |  | Agile Training
On-site or Virtual
A Journey Through an Agile/Scrum Project Lifecycle |  | Real World Agile for Teams - 3 day workshop
Thinking of Agile? Start Here |  | Agile for Executives and Leaders - 1 Day
Agile Visual Modeling Techniques |  | Agile for Product Owners - 2 Days
Agile Estimating and Planning |  | Agile Portfolio Management - 2 days
Agile vs. Traditional Roles |  | Agile Project Management - 2 or 3 days
More... |  | Agile Transformation Strategy Planning - 1-2 Days
Agile Requirements Gathering - 3 Days
Scrum 101 Videos |  | Servant Leadership - Leading High Performing Teams
Effective Facilitation and Collaboration Skills for Leaders
Scrum 101 – Part 1 ¦ Scrum Basics
Scrum 101 – Part 2 ¦ The Scrum Process
Scrum 101 – Part 3 ¦ Scrum Values
Scrum 101 – Part 4 ¦ Scrum Terms Review
High Performing Teams Video Series
Part 1 ¦ Foundations of High Performing Teams
Part 2 ¦ Team Maturity Stages
Part 3 ¦ Servant Leadership
Part 14 – Ten MUST Haves for Effective Meetings!
Watch the Series (17 videos)
Agile Teams Video Series
Advanced:
Agile Teams – Part 1 ¦ Team Characteristics | Transforming to an Agile PMO
Agile Teams – Part 3 ¦ The Product Owner Role | Agile Portfolio Planning with Kanban
Agile Teams – Part 4 ¦ The Scrum Master Role | Success Factors for Transitioning to Agile
Watch the Series (17 videos) | PMI ACP Certification
Agile Simulation Videos
Agile Simulation – Part 1 ¦ Meet the Agile Team
Agile Simulation – Part 2 ¦ Overview of the Agile Lifecycle
Agile Simulation – Part 3 ¦ Purpose, Agenda, Team Norms
Agile Simulation – Part 20 ¦ The Daily Standup
Watch the Series (23 Videos)
Blogs on Agile Topics
A Journey Through the Agile Lifecycle
The Four Levels of Agile Requirements
My Amazing Visit to Southwest Airlines!
Success Factors When Transforming to Agile
Answers to Top PMI Agile Certified Practitioner (PMI-ACP) SM Certification Questions
PMI Agile Certified Practitioner (PMI-ACP) SM Certification Study Tips
My PMI-ACP SM Certification Exam Retrospective

## Acceptance Tests
Acceptance Tests are core Agile requirements. I recommend that you document every business rule as a test case here in the format 'Verify that when <action occurs> <expected result>. Attach (or link to) a spread sheet with input/output expected data for stories that are data/reporting related.
Story | Acceptance Test ID | Acceptance Test Description | Accepted By | Accepted Date | Testing Notes
1.1 As a Customer I want to Login so that I can access my account | TC1 | Verify that customer with valid user name and password can login successfully
1.1 Customer Login | TC2 | Verify that customer with invalid user name cannot login and gets correct error message
1.1 Customer Login | TC3 | Verify that customer with invalid format for user name or password cannot login and gets correct error message
1.1 Customer Login | TC4 | Verify that customer who forgets to input user name or password gets correct error message
1.1 Customer Login | TC5 | Verity that different users in different roles can login and are forwarded to appropriate landing page

## Impediments
Total It 0: | 5 |  | Total It 2: | 0 |  | Total It 4: |  | 0
Total It 1: | 3 |  | Total It 3: | 0 |  | Total It 5: |  | 0
Iteration | Impediment | Severity (H, M, L) | Affects Story? | Assigned to Who for Follow-up? | Opened Date | Resolved Date | Open Days | Current State and Notes
0 | Waiting for John an answer to xyz business rule | M | 2.3 | John | 2008-02-12 | 2008-02-17 | 5 | John emailed me back a reply and cc'd Amy (BA) who documented the new rules
0 | [6 empty] | 0
0
0
0
1
1
1

## Capacity Planning
| Resource Capacity By Iteration |  |  |  | From | To | Working Days: |  | From | To | Working Days:
[5 empty] | 2007-12-12 | 2008-01-01 | 15 |  | 2012-01-01 | 2012-01-29 | 15
|  |  |  | Iteration 1 |  |  |  | Iteration 2
Resource Type | Core Team | Resource Names | % Allocation | # Days Off | Available Hrs | Planned Hrs | % Utilization | # Days Off | Available Hrs | Planned Hrs | % Utilization
Contractor | Intermediate Java Developer | John Smith | 100% | 1 | 112 | 100 | 89.29% | 0 | 120 | 100 | 83.33%
Employee | Sr Java Web Developer | Mary Smith | 100% | 0 | 120 | 135 | 112.5% | 0 | 120 | 135 | 112.5%
Employee | QA Tester | Alan Smith | 75% | 2 | 74 | 40 | 54.05% | 0 | 90 | 40 | 44.44%
Contractor | Scrum Master | Beth Smith | 80% | 1 | 88 | 0 | 0% | 0 | 96 | 0 | 0%
Employee | Business Analyst | Larry Smith | 65% | 0 | 78 | 55 | 70.51% | 1 | 70 | 55 | 78.57%
Employee | Product Owner | JoAnne Smith | 40% | 0 | 48 | 40 | 83.33% | 1 | 40 | 40 | 100%
Employee | Business User | Amy Adams | 50% | 0 | 60 | 65 | 108.3% | 0 | 60 | 65 | 108.3%
| Shared Resources |  |  |  | 0 | #VALUE! |  |  | 0 | #VALUE! | 0%
Employee | Architect (30%) | Ronnie Smith | 25% | 2 | 14 | 20 | 142.9% | 0 | 30 | 20 | 66.67%
Employee | Report Designer(10%) | Jackie Smith | 10% | 0 | 12 | 15 | 125% | 1 | 4 | 15 | 375%
Employee | ETL Resource (10%) | Doug Smith | 10% | 0 | 12 | 10 | 83.33% | 0 | 12 | 10 | 83.33%
Contractor | Portal Resource | Greg Smith | 30% | 2 | 20 | 15 | 75% | 0 | 36 | 15 | 41.67%
Employee | Business SME for XYZ system | Tom Smith | 25% | 0 | 30 | 30 | 100% | 1 | 22 | 30 | 136.4%
Employee | IT SME for XYZ System | Jonny Smith | 25% | 1 | 22 | 20 | 90.91% | 0 | 30 | 20 | 66.67%
Employee | DBA | Karen Smith | 40% | 0 | 48 | 15 | 31.25% | 0 | 48 | 15 | 31.25%
Listing the team members here and their contact information is helpful plus their allocation and planned days off is very useful. Using the iteration capacity and utilization planning is optional and could be used if the team finds it useful for them to plan their work. The best method for determining capacity is looking at previous velocity then adjusting for vacation or holidays.
Email me if you have questions about what the data in this worksheet means. Sally@AgileTraining.com
Iteration Capacity Map Worksheet
Use the table below to map out each story into the sub-deliverables (tasks/milestones) through the course of your iteration so you can plan your capacity and commitements better as a team. Color code the different type of work (req, desgin, dev, testing, uat..). This is best done on a physical visible wall.
| Column1 | Column2 | Column3 | Column4 | Column5 | Column6 | Column7 | Column8 | Column9 | Column10 | Column11
Iteration #: 5 (2 wks)
Stories | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10
1.1 As a manager I want to .. So that..
1.2 As a supervisor I want to .. So that..
Velocity Avg by Team
|  |  | Team A | Team B | Team C | Team D
|  | Q1 | 475 | 200 | 350 | 150
|  | Q2 | 400 | 250 | 390 | 230
|  | Q3 | 435 | 275 | 425 | 200
|  | Q4 | 450 | 260 | 400 | 245
|  | Yearly | 1760 | 985 | 1565 | 825
Note on G4: Sally: identified during planning meeting
Note on K4: Sally: identified during planning meeting
Design and Code TC1,2,3 - AJ
Test TC1, TC2
- Shri
UAT TC1,2,3
Design and Code TC4-6 - AJ
Update Req/UAT Doc - Jen
Test TC1, TC2
- Shri
UAT TC4,5,6
Deploy
Deploy
Design Review
Automate xyz
- Lilly
UAT xyz
Design and Code xyz - Adam
Update Req/UAT Doc - Jen
Test abc - Shri
UAT abc
Deploy
Deploy
Code abc - Adam
Sprint Review and Final Acceptance
Sprint Demo & Retrospective | Sprint Planning

## Monthly Budget
Sample PROJECT |  |  |  | Month | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Total
Resource Type | Core Team | Resource Names | Hrly Rate | Estimated Workdays | 21 | 20 | 21 | 20 | 21 | 20 | 20 | 22 | 18 | 22 | 19 | 19 | 243
Employee | Product Owner | Augustin | 0 | 50% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee | Team Lead | Jeff | 0 | Month: 100%; Jan: 0; Feb: 0; Mar: 0; Apr: 0; Total: 0
Employee | QA Lead | Lisa | 0 | Month: 100%; Jan: 0; Feb: 0; Mar: 0; Apr: 0; Total: 0
Employee | QA Lead | Haritha | 0 | 100% |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vendor B | Scrum Master | Susan | 0 | 50% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vendor B | Business Analyst | Susan | 0 | 50% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Employee | Business User | Marry | 0 | 38% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Vendor A | Team Lead | Elena | 40 | 100% | 6720 | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 | 7040 |  |  | 65600
Vendor A | Team Lead | Reney | 40 | 100% | 6720 | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 | 7040 |  |  | 65600
Vendor A | Sr. Developer | Igor | 40 | 100% | 6720 | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 | 7040 |  |  | 65600
Vendor A | QA | Kumar | 40 | 100% | 6720 | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 |  |  |  | 58560
Vendor A | Developer | Melissa | 40 | 100% | 3360 | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 |  |  |  | 55200
Vendor A | Developer | Elexa | 40 | Month: 100%; Jan: 3360; Feb: 6400; Mar: 6720; Apr: 6400; Total: 22880
Vendor A | QA | Alex | 40 | 100% |  | 6400 | 6720 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 | 7040 |  |  | 58880
Vendor A | Developer | Sathia | 40 | 100% |  |  | 3360 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 |  |  |  | 42080
Vendor A | Developer | Adam | 40 | 100% |  |  | 3360 | 6400 | 6720 | 6400 | 6400 | 7040 | 5760 |  |  |  | 42080
Vendor A | Sr. Developer | Ajay | 40 | Month: 100%; Apr: 3200; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 35520
Vendor A | Sr. Developer | Peter | 40 | Month: 100%; Apr: 3200; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 35520
Vendor A | Sr. Developer | Ema | 40 | Month: 100%; Apr: 3200; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 35520
Vendor A | Developer | Yani | 40 | Month: 100%; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 32320
Vendor A | Developer | Yrui | 40 | Month: 100%; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 32320
Vendor A | QA | Julia | 40 | Month: 100%; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 32320
Vendor A | QA | Robert | 40 | Month: 100%; May: 6720; Jun: 6400; Jul: 6400; Aug: 7040; Sep: 5760; Total: 32320
Vendor A | QA | QA | 40 | Month: 100%; Jul: 6400; Aug: 7040; Sep: 5760; Total: 19200
Vendor A | Performance QA | Adam | 40 | 100% |  | 1280 | 1344 | 1280 | 1344 | 1280 | 1280 | 1408 | 1152 | 1408 |  |  | 11776
Employee | DBA | Chris | 0 | 10% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
Forecast Per Month |  |  |  |  | 33600 | 46080 | 55104 | 68480 | 102144 | 97280 | 97280 | 107008 | 70272 | 29568 | 0 | 0 | 706816
Actual Per Month |  |  |  | Jan: 26196; Feb: 40199; Mar: 41416.79; Apr: 60754; May: 77872.54; Jun: 83962
Variance |  |  |  |  | 7404 | 5881 | 13687.21 | 7726 | 24271.46 | 13318 | 97280 | 107008 | 70272 | 29568 | 0 | 0
Cumulitive Forecast |  |  |  |  | 33600 | 79680 | 134784 | 203264 | 305408 | 402688 | 499968 | 606976 | 677248 | 706816 | 706816
Actual/Forecast |  |  |  |  | 26196 | 66395 | 107811.79 | 168565.79 | 246438.33 | 330400.33 | 444200.33 | 558248.33 | 651560.33 | 681128.33 | 681128.33
1 QA & 2 Dev only 50% of May

## Tasks (hidden)
[5 empty] | Task Burndown Totals: |  | 40503 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Iteration 1
Story (linked) | Tasks: Enter descriptions below, 1 per task. Enter each day's remaining hrs at right. Each column is sortable. Burndowns automatically update. | Resources (linked) | TaskType | Status | Notes | Hrs Est | 0 | 1899-12-31 | 1900-01-01 | 1900-01-02 | 1900-01-03 | 1900-01-04 | 1900-01-05 | 1900-01-06 | 1900-01-07 | 1900-01-08 | 1900-01-09 | 1900-01-10 | 1900-01-11 | 1900-01-12 | 1900-01-13 | 1900-01-14 | 1900-01-15 | 1900-01-16 | 1900-01-17 | 1900-01-18 | 1900-01-19
1.1 Customer Login | develop screen | John Smith |  |  |  | 7 | 2010-11-21
1.1 Customer Login | add security | John Smith |  |  |  | 16
1.1 Customer Login | user acceptance testing | Mary Smith |  |  |  | 110
1.1 Customer Login | document business rules and test cases | Jackie Smith |  |  |  | 15
Note on H4: Sally: Every day a task in progress, the person should give their Commit Date (when they think it will be done). Not hours remaining!

## Story Complexity (hidden)
Story Complexity Breakdown | [9 empty] | 1 = Very Small 2 = Small 3 = Medium 5 = Med-Large 8 = Large 13 = Very Large 21 = EPIC
The purpose of this sheet is to help the team estimate story points for each story during initial release planning. The team is using the 'Complexity Buckets Method' for sizing. Feel free to change the complexity columns based on your project needs. Track the team notes so you can understand what assumptions were made during the sizing sessions.
Story | Final Points | UI Complexity | Points2 | Business Rules/Logic Complexity | Points3 | DB/Integration Complexity | Points4 | Testing Complexity | Points5 | Notes
1.1 Customer Login | 3 | Light, just one screen and minor fields | 1 | Not much buisness logic | 1 | no db | 0 | light testing | 1
1.2 Customer registers for new online account | 5 | Medium, this screen has more fields and more involved on screen validation | 2 | we do have business logic here to validate duplicate registrations, age ..etc but still light | 1 | there are several tables that have to be updated to save a new customer so this is medium complexity. | 2 | testing is light but should cover testing all the negative and positive business rules. | 1
Note on B5: Sally: Team totals all the bucket points then decides which final bucket to throw the story in.

## Risks
RISK | HOW IS IT ADDRESSED? | Severity | Iteration Identified | Iteration Addressed
Resources. I still don't have a mainframe developer | Raised risk to manager of mainframe area and stakeholder group. Will impact us for iteration 2 if not resolved by then. | High | 0
The team is new to Portlet Factory. Many of them don't know how to use it. | Director has agreed to send team to training during iteration 2 | High | Release Planning | 2
We have never integrated with XYZ system before. This is our first time sending that system a file from the Java side. | Proof of Concept story identified in Iteration 0. Scheduled for Iteration 1. | High | 0 | 1

## Definition of Done
Our Definition of 'DONE'
Story Level
Pass unit testing on workstation (developer verifies all user test cases pass)
All code checked in and tagged in version control correctly (iteration # and story #)
Code review completed | This is is just an example, fill out your own for your team. You can also have a definition of done for each column of your Kanban wall. The Definition of Done should be kept visible in your team area.
Brand Applied to each page
All acceptance test cases have passed
User tested and accepted in Test Integration Enviroment
Iteration Level
No Severity I or II Defects
Release Level
All Process Change Management stories 'Done'
No Severity I or II Defects

## Dependency
Very important artifact to produce during release planning to have a visual view of what features/stories depend on the others. It guides you on which stories need to be developed upfront.
If your features/stories have a high dependency on each other then you can use this tab to take a picture of your dependency chart to help guide your release planning effort. This is is just an example, fill out your own for your team.

## Documentation List
Every company has specific deliverable artifacts that must be produced for each project team. This would a place to link/track all of them. These could be very light or heavy depending on your current organization constraints/policies. Agile suggests that we only document what is valuable and will be used.
Deliverable/Document/Artifact | Description
Project Charter | Includes business case, vision statement, conditions of satisfaction, high level scope, initial non functional requirements
Organization Chart | Who is who on the project and their contact
"As is" & "To be" Process Diagrams | Created during initial release planning or iteratoin 0. Very valuable if they help you define the scope of the project. | This is is just an example, fill out your own for your team.
Use Case Diagrams | Define who does what and outlines the roles we are trying to serve from this system
User Roles and Personas | Detailed definition of the attributes, characteristics, usability requirements of each target role.
Procurement Plan | If software/hardware needs to be procured
Work Plan | PMBOK
Change Management Plan | How will scope changes be tracked and managed? What types of changes will be tracked? Who is responsible for tracking this?
Cost Benefit Analysis (CBA) | ROI/Business Value Points vs Story Points and cost analysis.
Charter Approval | Signed Docs (if your process requires this)
High Level Architecture | Software Architecture and System Integration developed during release planning and iteration 0. Very important.
Project Plan Approval | if your processes requires this.
RAM | Resource Assignment Matrix (this is similar to the Resources tab)
Agile Workbook | Used for managing daily work activity (this artifact)
SAR | System Architecture Review (documentation and approval of any new architecture components/software/technologies and a plan for how to deploy, maintain and use them)
Business Rules | link to any business rule specific docuementation
Closure Report | PMBOK
Transition Report | PMBOK
Archive Project Artifacts
Promotion Request Package (PRP) | (list all the change control numbers to migrate code to prod) (recommend generating a PRP per Development Iteration) (prp per system(s) depending on if each system requires a separate PRP or not)
Note on B11: Sally: Business value points are a very important measure you should track. Email me for a cheat sheet on this. sally@agiletransformation.com

## Legend
Iteration | Story | Resources | Task Types | Status Types | Goals | Business Value
0 | Linked from | Linked from | Analysis | To Do | Done | High
1 | Feature List tab | Resources tab | Dev | In Progress | Done-Carryover | Medium
2 |  |  | DB | Blocked | Not Done | Low
3 |  |  | Testing | Done | Progress
4 |  |  | Follow-Up | Cancelled
5
Instructions for hiding/unhiding sheets
XP: | Go to Format -> Sheet -> Unhide to review any sheets (tabs) that are not visible.
Vista: | Home Tab>Cells>Format>Visibility and click Hide & Unhide